## Project Map
ID | Description | Party Responsible
|  | Partner | Client | Insight Works
Step 1: Project Prerequisites
The following steps must be completed before Step 6: Insight Works Discovery
1.1 | Warehouse Insight Training Prerequisites
1.1.1 | Identify warehouse processes. | ✓ | ✓
1.1.2 | Business Central – Configure, implement and training on the base Warehouse module. | ✓ | ✓
1.1.3 | Business Central – Test base NAV/BC Warehouse module by posting relevant transactions (picks, shipments, receipts, etc.) | ✓ | ✓
1.1.4 | Business Central – Verify base Warehouse module has test data. | ✓ | ✓
1.2 | Dynamic Ship Training Prerequisites
1.2.1 | Set up EasyPost account. | ✓ | ✓
1.2.2 | Business Central – Verify sales order is ready to ship as test data (if not using warehousing). | ✓ | ✓
1.2.3 | Business Central – Verify Warehouse shipment is created, picked, and ready to ship (if using warehousing). | ✓ | ✓
1.3 | Shop Floor Insight Training Prerequisites
1.3.1 | Business Central – Set up resources (if using time for jobs). | ✓ | ✓
1.3.2 | Business Central – Ensure Jobs can be created and Job Journals can post resource costs to them (if using time for jobs). | ✓ | ✓
1.3.3 | Business Central – Ensure released production orders can successfully post time, output, and consumption without errors. | ✓ | ✓
1.3.4 | Business Central – Ability to post with the Output Journal. | ✓ | ✓
1.3.4 | Business Central – Ability to post with the Consumption Journal. | ✓ | ✓
1.3.5 | Business Central – Verify that relevant test data created. | ✓ | ✓
1.4 | Product Configurator Training Prerequisites
1.4.1 | Identify sales processes (if using with sales documents). | ✓ | ✓
1.4.2 | Identify production order processes (if using with production orders). | ✓ | ✓
1.4.3 | Business Central - Set up component items and work centers (if using with production orders). | ✓ | ✓
1.4.4 | Business Central - Set up production BOMs and routings to support production order processes (if using production orders). | ✓ | ✓
1.4.5 | Business Central - Ensure released production orders can be processed using sample data and the results from posting meet both operational and costing requirements (if using production orders). | ✓ | ✓
1.4.6 | Identify assembly order processes (if using with assembly orders). | ✓ | ✓
1.4.7 | Business Central - Set up component items and resources (if using assembly orders). | ✓ | ✓
1.4.8 | Business Central - Set up sample assembly BOM(s) to support assembly order processes (if using assembly orders). | ✓ | ✓
1.4.9 | Business Central - Ensure assembly orders can be processed using sample data and the results from posting meet both operational and costing requirements (if using assembly orders). | ✓ | ✓
1.5 | Enhanced Planning Pack Training Prerequisites
In order to use the Enhanced Planning Worksheet component of the EPP you should:
1.5.1 | Ensure your Manufacturing Setup is complete (especially the Numbering and Planning FastTabs). | ✓ | ✓
1.5.2 | Ensure your BC item or SKU planning parameters are setup. | ✓ | ✓
1.5.3 | Ensure you have a forecast setup if you will be using one. | ✓ | ✓
1.5.4 | An easy way to check these steps are done and working is to run the standard BC Planning Worksheet and ensure you are getting planning suggestions. | ✓ | ✓
1.5.5 | If planning to use this it is probably best if users have already received training on the base BC Planning Worksheet or at least be familiar with how BC’s MRP works. | ✓ | ✓
In order to use the Enhanced Forecast Worksheet:
1.5.6 | You will need sufficient item ledger entries of type sale (the system uses the Posting Date, Item, and Quantity). | ✓ | ✓
1.5.7 | Ensure the forecasting model setup will also need to have been completed, which I think we would typically do during the extension installation. | ✓ | ✓
Additional requirements:
1.5.8 | In order to use the Item Planning Review you will need sufficient item ledger entries. | ✓ | ✓
1.5.9 | In order to use the Routing Analysis you will need to have routings setup along with having posted production times through the output or production journals and also finished production orders. | ✓ | ✓
1.5.10 | In order to use the Multi-Level BOM you will need to have created production bills of material. | ✓ | ✓
1.6 | MxAPS Training Prerequisites
1.6.1 | Business Central – Ensure work centers and shop calendars are setup. | ✓ | ✓
1.6.2 | Business Central – Ensure machine centers are created for any work centers that have a capacity of more than 1. | ✓ | ✓
1.6.3 | Business Central – Ensure routings are setup and contain setup and/or run times. | ✓ | ✓
1.6.4 | Business Central – Ensure production bills of material are setup if necessary. | ✓ | ✓
1.6.5 | Business Central – Ensure released production orders can successfully post time, output, and consumption without errors. | ✓ | ✓
1.6.6 | Business Central – Ensure that a representative amount and item mix of production orders have been created. | ✓ | ✓
Step 2: Project Initiation
2.1 | Place software order with Insight Works. | ✓ | ✓
2.2 | Complete kick-off documents. | ✓ | ✓
2.3 | Order scanners from Insight Works if required. |  | ✓ | ✓
2.4 | Create Insight Works project ticket (use this ticket for all install/setup communication). | ✓ | ✓ | ✓
2.5 | Schedule discovery via the provided links (1 to 2 weeks before training). | ✓ | ✓
2.6 | Schedule training via the provided links (1 to 2 weeks after discovery). | ✓ | ✓
Step 3: Set Up Existing Environment
The following steps apply to Testing/Staging and Production environments.
3.1 | Update NAV/BC license with Insight Works products (On Premises Only). | ✓ | ✓
3.2 | Provide Insight Works with administrative access (On Premises Only). | ✓ | ✓
3.3 | Provide a user account with super user access to Insight Works. | ✓ | ✓
3.4 | Provide remote access to test/staging Environment via install ticket (use www.isafesend.com for passwords). | ✓ | ✓
3.5 | Provide remote access to on premises service server (only if On Premises WHI and or using IIS). | ✓ | ✓
3.6 | Provide remote access to on premises service server (always Shop Floor Insight). | ✓ | ✓
Step 4: Review of Existing Environment
4.1 | Verify remote access. |  |  | ✓
4.2 | Verify administrative access (On premises only). |  |  | ✓
4.3 | Verify Business Central super user access. |  |  | ✓
4.4 | Verify service account licensing/users (require User or Device License). | ✓ | ✓ | ✓
4.5 | Address possible issues with environment via install ticket (see Step 2). | ✓ | ✓ | ✓
Step 5: Insight Works Products Implementation and Configuration
5.1 | Install Insight Works products. |  |  | ✓
5.2 | Identify/merge conflicting Business Central modifications (if required). |  |  | ✓
5.3 | Configure product on the test/staging environment. |  |  | ✓
5.4 | Configure scanner device (Emulator). | ✓ | ✓ | ✓
5.5 | Train customer IT staff remotely to connect scanner devices when they arrive on-site. |  |  | ✓
5.6 | Verify any label printers are working (any configuration / troubleshooting is billable T&M) | ✓ | ✓ | T&M
Step 6: Insight Works Discovery
Discovery will need to be rescheduled if the pre-requisites have not been completed (see Step 1)
6.1 | Warehouse Insight (required). | ✓ | ✓ | ✓
6.2 | Dynamic Ship (required). | ✓ | ✓ | ✓
6.3 | Shop Floor Insight (required). | ✓ | ✓ | ✓
6.4 | Configurator (required)
6.5 | Identification of modifications (if required). | ✓ | ✓ | ✓
Step 7: Insight Works Product Training (Train the Trainer)
7.1 | Product training and consulting. |  | ✓ | ✓
7.2 | Identify modifications (support@dmsiworks.com). |  | ✓ | ✓
Step 8: Products Modifications (if required)
8.1 | Modify design and quotation (1-3 weeks depending on resources) (billable T&M). |  |  | T&M
8.2 | Modify development (1-3 weeks depending on resources) (billable T&M). |  |  | T&M
Step 9: UAT Phase
9.1 | Develop test case scenarios. | ✓ | ✓
9.2 | Conduct user testing based on test scenarios. | ✓ | ✓
9.3 | Insight Works will provide UAT support as required (support@dmsiworks.com). | ✓ | ✓ | ✓
9.4 | Identify modifications (support@dmsiworks.com) | ✓ | ✓ | ✓
9.5 | Submit go-live ticket (support@dmsiworks.com) (requires 5 business days’ notice). | ✓ | ✓
Step 10: Go Live
10.1 | Move Business Central objects from the test system to the production system. |  |  | ✓
10.2 | Move Business Central configuration from the test system to the production system. |  |  | ✓
10.3 | Reconfigure service tier or install a new service tier (dependent on the client’s server setup). |  |  | ✓
10.4 | Reconfigure the devices to refer to the new company and service tier. | ✓ | ✓ | ✓
10.5 | Conduct a smoke test with the devices to verify connectivity with Business Central. |  | ✓ | ✓
10.6 | Post Go-Live Support (billable T&M) | ✓ | ✓ | T&M